## Vision and Roadmaps Exercise
Part 1 Instructions: Using the columns A and B determine the target population and intended outcome for each company based on their vision.
Company | Vision | Target Market/Population | Intended Outcome
Nike | Bring inspiration and innovation to every athlete in the world | Every athlete in the world | Bring inspiration and innovation
LinkedIn | To connect the world’s professionals to make them more productive and successful. | The world's professionals | Connect and make more productive and successful
ASOS | To become the number 1 fashion destination for 20-somethings globally. | 20-somethings globally | Become the number 1 fashion destination
Microsoft | Our mission is to empower every person and every organization on the planet to achieve more. | every person and every organization | empower and allow to achieve more

## Mangaging the Backlog Exercise
Instructions: Using progressive elaboration and the INVEST criteria, assign the user stories to the “Top of the backlog” or the “Bottom of the backlog” based on the information provided in the spreadsheet. Use the information from columns A and B to decide if the user story should be in the top or bottom of the backlog by selecting Top of the Backlog or Bottom of the Backlog in column C.
User Stories | Info about User Story | Answer
User Story 1 | Depends on story 7 | Bottom of the Backlog
User Story 2 | Team has never done this type of work before | Top of the Backlog
User Story 3 | Story is detailed and ready to implement | Top of the Backlog
User Story 4 | Story can not be tested | Bottom of the Backlog
User Story 5 | Story is small and testable | Top of the Backlog
User Story 6 | Story is too big to implement | Bottom of the Backlog
User Story 7 | Story has no dependencies and the team has a good understanding of the story. Story is sized appropriately | Top of the Backlog
User Story 8 | The team has alot of uncertainty with completing this user story. | Top of the Backlog
User Story 9 | This is a critical user story that is well understood and appropriately sized but has a dependency on User story 3 | Bottom of the Backlog
User Story 10 | This is a critical user story that is well understood and appropriately sized and has no dependencies | Top of the Backlog

## Prioritization Exercise
Instructions: You are buying a new car for your family of 7. Prioritize the list of features for your new car using the MoSCoW prioritization method. Use the dropdown list in column B to select the corresponding letter (M,S,C,W) from the MoSCoW method beside the item.
Car Features | Priority
Tires Installed | M
Seatbelts Included | M
Color: Black | C
Sunroof | C
Able to seat 7 people | M
Coffee Maker | W
Chrome rims | C
V6 Engine | W
V8 Engine | W
Refrigerator | W
Panoramic Roof | W
Radio | M
Radio with Bluetooth | M
Navigation | M
Trailer Hitch | W
Steering Wheel Included | M
Brakes | M

## Scoping & Estimation Exercise
Instructions: Assign each animal listed one of the numbers from the list of numbers provided in the dropdown of column B based on relative size, scope, complexity to each other.
Animal | Number Assignment
Elephant | 100
Giraffe | 8
Lion | 13
Yorkshire Terrier | 2022-01-02
Bull Mastiff | 2
Fox | 1
Hippopotamus | 40
Tiger | 20
Black Bear | 3
Mouse | 0

## Release & Iteration Planning Ex
Instructions: Calculate the velocity for each team in columns A & B. Then use this data to help answer the questions in the classroom.
Sprints | Team A | Team B
Sprint 1 | 12 | 31
Sprint 2 | 20 | 23
Sprint 3 | 16 | 19
Sprint 4 | 18 | 25
Sprint 5 | 17 | 24
Velocity | 17 | 24