## 1. Scrum Exercise
What is the established velocity of the team?
Part 1
Sprint 1 | 27
Sprint 2 | 23
Sprint 3 | 25
Total | 75
Avg | 25
How many sprints will it take to complete all the work?
Part 2
Velocity | 25
Story Points | 112
Sprints | 5
Answer

## 2. Escaped Defects Exercise
What is the escaped defects % for team 1 and team 2
Team 1 Environment | # of bugs | % of bugs found
Dev | 835 | 63.11%
Staging | 421 | 31.82%
Production | 67 | 5.064%
Total | 1323
Team 2 Environment | # of bugs | % of bugs found
Dev | 124 | 95.38%
Staging | 5 | 3.846%
Production | 1 | 0.7692%
Total | 130

## 3. Using Metrics
Use the data below and create at least three charts that will help the team answer the following questions: - Is the team delivering consistently? - Is the team's original delivery estimate accurate? - How many story points is the team delivering in each sprint? - What should the team commit to deliver in future sprints?
Sprint | Story Point Completed | Points remaining | Cumulative Points Completed
Sprint 0 | 0 | 80 | 0
Sprint 1 | 19 | 61 | 19
Sprint 2 | 21 | 40 | 40
Sprint 3 | 19 | 21 | 59
Sprint 4 | 21 | 0 | 80
Velocity
20

## 4. Continuous Improvement
Use the data below to create a Committed vs Delivered Chart
Sprint | Committed | Delivered | % Committed vs Delivered
Sprint 1 | 25 | 20 | 125%
Sprint 2 | 25 | 18 | 138.9%
Sprint 3 | 30 | 20 | 150%
Sprint 4 | 25 | 20 | 125%
Sprint 5 | 30 | 25 | 120%
Sprint 6 | 20 | 20 | 100%
Create Chart Below

## 5. Simple BVIR
Use the provided Metrics below to figure out and create the following: - Burn Down & Chart - Burn Up & Chart - Average Velocity over 5 Sprints - Expected Completion Sprint (BVIR)
Sprint | Committed Story Points | Delivered Story Points | Remaining Story Points | Cummulative Story Points Completed
Sprint 0 | 0 | 0 | 122 | 0
Sprint 1 | 20 | 21 | 101 | 21
Sprint 2 | 21 | 21 | 80 | 42
Sprint 3 | 22 | 20 | 60 | 62
Sprint 4 | 22 | 21 | 39 | 83
Sprint 5 | 21 | 21 | 18 | 104
Sprint 6
Average
Burn Down
Burn up Chart
Velocity Chart
20.8 | Always round down value = 21
BVIR | Create a BVIR below that helps to show the expected completion sprint using charts from above. You can copy them here to Create your BVIR. If you want to add text, do so in the cells surrounding the space below.

## 6. Measuring Progress
Use the data below to complete the following: - Burn Down Metrics & Chart - Burn Up Metrics & Chart - Velocity Metrics & Chart
Sprint | Committed Story Points | Delivered Story Points | Remaining Story Points | Cumulative Story Points Completed | % Committed vs Delivered
Sprint 0 | 0 | 0 | 64 | 0
Sprint 1 | 25 | 20 | 44 | 20 | 125
Sprint 2 | 20 | 22 | 22 | 42 | 90.9091
Sprint 3 | 22 | 22 | 0 | 64 | 100
Average
Burn Down Chart
Burn Up Chart
Average Velocity
21.3333 | 21
BVIR

## 7. Quality Metrics
Create a chart to display the quality rate over time
Month | Quality Rate | Goal | High
January | 98.3% | 98% | 100%
February | 98.1% | 98% | 100%
March | 98% | 98% | 100%
April | 97% | 98% | 100%
May | 96% | 98% | 100%
June | 96.5% | 98% | 100%
Quality Metrics Chart
Create selecting Month, Quality Rate and Goal. All the rest is default. If you use MS check: https://classroom.udacity.com/nanodegrees/nd144/parts/cd0006/modules/859eb994-ce9d-407a-a141-e3efeba6541f/lessons/b7f54535-7631-4b68-a0eb-089e7e2047e2/concepts/8483c9ac-e70f-4f51-8b8f-a6647278f225

## 8. Failure Patterns
Create a Quality chart and a Velocity chart
Sprint | Quality Rate | Goal
1 | 98.3% | 98%
2 | 97.45% | 98%
3 | 97.75% | 98%
4 | 96.5% | 98%
5
6
7
Quality Chart
Sprint | Story Points Completed | Story Points Remaining
0 | 0 | 130
1 | 20 | 110
2 | 21 | 89
3 | 19 | 70
4 | 25 | 45
5 |  | 45
6 |  | 45
7 |  | 45
Velocity Chart

## 9. Agile Communication
Use the data to create one or more charts to communicate what is currently happening with the project. CHALLENGE! Can you use both data tables in one chart?
Sprint | Story Points Completed | Story Points Remaining
0 | 0 | 250
1 | 37 | 213
2 | 76 | 137
3 | 37 | 100
4 | 55 | 45
Sprint | Quality Rate | Goal
1 | 98.3% | 98%
2 | 93% | 98%
3 | 97.75% | 98%
4 | 96.5% | 98%
Chart(s)

## 10. Reviewing Performance
Use the data provided by the Product Owner to create a Committed vs Delivered Chart
Sprint | Committed | Delivered | % Committed vs Delivered
1
2
3
4
5
6