## Burn Down Chart
Sprint	Story Points Remaining	Story Points Completed
Sprint 0	100	0
Sprint 1	77	23					Make a graph selecting the columns Sprint and Story Points Remaining:
Sprint 2	51	26
Sprint 3	29	22
Sprint 4	0	29
Burn Down Chart

## Committed Vs Delivered
Sprint	Committed	Delivered	% Committed Vs Delivered
Sprint 1	25	19	131,58
Sprint 2	25	20	125
Sprint 3	30	21	142,86
Sprint 4	25	20	125
Sprint 5	20	19	105,26
Sprint 6	20	21	95,24

Velocity = Story Points / Number of sprints
Committed Vs Delivered Chart