## Product Roadmap
Instructions: Based on the scenario, place the Product Features into the phases on the Product Roadmap. The product features should be orderd so that the highest value features are delivered to users first and the simple to implement features are delivered before the more complex features. The product Features are listed in Column A. Each Cell in the four phases of the Product Roadmap has a dropdown list that allows you to select the product features that you want to appear in that phase of the roadmap. Every feature must be added to a Phase of the roadmap.
Product Feature List | Phase 1 | Phase 2 | Phase 3 | Phase 4
Initial Architecture/Database Setup & Design | Initial Architecture/Database Setup & Design
Develop iOS Compatible Mobile App |  |  | Develop iOS Compatible Mobile App
Develop Android Compatible Mobile App |  |  | Develop Android Compatible Mobile App
Develop Web Portal application |  | Develop Web Portal application
Upgrade Database |  |  |  | Upgrade Database
Security Update |  |  |  | Security Update
Manual Importing | Manual Importing
Automated Integration for Importing |  |  |  | Automated Integration for Importing
Mobile App User Interface Refinement |  |  | Mobile App User Interface Refinement
Authentication- Login/Logout | Authentication- Login/Logout
Basic Dashboard with heatmap display | Basic Dashboard with heatmap display
Basic Data Searching Capability |  | Basic Data Searching Capability
Automated Amber Alerts |  |  | Automated Amber Alerts
Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities |  |  | Customizable/Interactive Dashboard with heatmaps, bar charts, and zooming capabilities
User Based Preferences- Save Search & Reports |  | User Based Preferences- Save Search & Reports
Web Portal Redesign |  |  |  | Web Portal Redesign
Export CSV of Reported Data |  | Export CSV of Reported Data
Send Manual Amber Alerts by Region |  | Send Manual Amber Alerts by Region
Web Report of Data (View only no Export) | Web Report of Data (View only no Export)
In-App messaging for Doctors and Patients |  |  |  | In-App messaging for Doctors and Patients

## User Roles
Instructions: Below are 7 user roles that have been identified for the product and a brief description for how each user will interact with the product. These user roles can be used to create user stories in the blue "User Story" tab.
Roles | Personas
CDC Officials | Will use product to determine where to apply funding and send test kits
System Administrators | Responsible for governing all roles of the product. This role is not a health professional. This role maintains and governs the system, the process, and does troubleshooting if other users have problems with their roles and access. This role also publishes product information and ensures that the system is performing as intended.
Patients | Will use the product to report, track, and monitor cases of the outbreak
Test Centers | Will use the product to report test kit usage
Doctors | Will use the product to share successful treatment remedies
Medical Examiners | Will use the product to report deaths caused by outbreak
Healthcare Companies | Will use the product to report test kit production and deliveries

## User Stories
Instructions: Create User Stories and Acceptance Criteria in the sheet using the 7 user roles that have been identified in the yellow user role tab. Two user stories have been provided for you for each role. Create at least 2 more user stories for each role based on the needs of each user. You will have at least 28 total user stories when finished. List at least 2 acceptance criteria for each User Story
As a.. | ....I can... | ...so that... | Completed User Story | Acceptance Criteria (Minimum of 2)
CDC Official | view the number of patients that have reported testing positive | so that I can analyze the outbreak | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | -Patient names are anonymous -User can see a summary of the numbers provided -User must be logged in from a government IP address to view
CDC Official | see a report of the # of test kits that health care companies have created | that I can send funding | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | -User can see a summary of the total number of test kits -User can see a summary of the number of test kits produced by healthcare company -User can see the names of the health care company -User can see amount of funds sent to each health care company
Doctor | add the name of patients I have treated | I can add treatments | As a Doctor I can add the name of patients I have treated so that I can add treatments . | -Alpha Numeric characters are allowed -Patient First and Last Name required -Patient DOB required -Patient Location Required -Patient Gender is optional
Doctor | login to the system | I can enter patient treatment information | As a Doctor I can login to the system so that I can enter patient treatment information. | -User name and email address required -User is locked out after 3 incorrect entries
Healthcare Company | add the number of test kits produced | the CDC can determine where test kits should be sent | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | -Only numeric characters allowed -User can see data that previously entered
Healthcare Company | reset my password by myself | that I can login again. | As a Healthcare Company I can reset my password by myself so that that I can login again. . | -User must verify email address -User must verify answer security question to reset password
Medical Examiner | add a person's gender | deaths can be tracked by gender | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | -User can select from list of genders -User can update gender selection -Users gender selection is not shared with CDC Officials
Medical Examiner | am automatically logged out of the system | no one can access my account | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | -Timeout occurs after 15 mins of inactivity -After timeout user is returned to login page
Patient | change my test results | the system data is accurate | As a Patient I can change my test results so that the system data is accurate. | -User can modify test results twice -Doctors are notified when a patient changes test results
Patient | enter any stores that I visited 3 days before testing positive | others are aware of their potential exposure to the virus | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | -Option only visible for patients that report positve test -Can specify store name, date entered, city, and state
System Administrator | give access to the system | users can access,import, share data. | As a System Administrator I can give access to the system so that users can access,import, share data.. | -First and Last Name required -Enter email addresses -Gmail email address are not allowed access
System Administrator | remove access | users are not able to access the system | As a System Administrator I can remove access so that users are not able to access the system. | -Removed user recieves email confirmation of removal -Removed user can't login once removed -System administrator must confirm the user that they are removing before leaving the page
Test Center | update/change the number of test kits recieved | data is accurate | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | -Only allow update one time -Make user confirm change before leaving the page
Test Center | I want to be notified when my stock falls before a certain level, | I can proactively order additional testing supplies | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | -System notifies user by email -User can set number that stock must reach for email to be sent -System notifies user upon login that stock is low
Patient | report that I contracted the virus | data is accurate | As a Patient I can report that I contracted the virus so that data is accurate. | 1) System confirms the report to the user by email 2) System explains to the user how to read general medical advices provided
Patient | read general advice written by professionals | I always have a medical reference about symptoms and potential cure / behavior to adopt | As a Patient I can read general advice written by professionals so that I always have a medical reference about symptoms and potential cure / behavior to adopt. | 1) System allows to search for the symptoms 2) System provides a hotline number for emergencies
CDC Official | see the heat maps of the outbreak | new proactive strategies can be planned accordingly | As a CDC Official I can see the heat maps of the outbreak so that new proactive strategies can be planned accordingly. | 1) User can search for town / area, System will show it on the map 2) System allows to zoom in / out
CDC Official | send funding to a specific area | funds can be used to stop the virus spreading in that area | As a CDC Official I can send funding to a specific area so that funds can be used to stop the virus spreading in that area. | 1) User can start the fund sending process directly from the heat maps report 2) User has a report page containing all the funds sent previously
Doctor | report the number of death caused by the virus | data is accurate | As a Doctor I can report the number of death caused by the virus so that data is accurate. | 1) User can report the number of death caused by virus 2) User can generate reports relate to the number of death caused by the virus for the previous months / years
Doctor | write and update professional medical advice that will be available to patients | patience have a medical reference about symptoms and potential cure / behavior to adopt | As a Doctor I can write and update professional medical advice that will be available to patients so that patience have a medical reference about symptoms and potential cure / behavior to adopt. | 1) User can create / delete / update the provided medical advice 2) User can check the previous version of a medical advice in the medical advice's history
Healthcare Company | report a change in the expected future production of tests | the CDC can take corrective actions in advance | As a Healthcare Company I can report a change in the expected future production of tests so that the CDC can take corrective actions in advance. | 1) Healthcare company can report a problem in production that can lead to a different number of test produced 2) Healthcare company can update the reported problem in case of change
Healthcare Company |  |  | As a Healthcare Company I can so that .
Medical Examiner |  |  | As a Medical Examiner I can so that .
Medical Examiner |  |  | As a Medical Examiner I can so that .
System Administrator |  |  | As a System Administrator I can so that .
System Administrator |  |  | As a System Administrator I can so that .
Test Center |  |  | As a Test Center I can so that .
Test Center |  |  | As a Test Center I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .

## Priority
Instructions: All of the user stories that you created will automatically appear in this sheet. Prioritize the user stories so that the highest value features are delivered to users first using the following parameters: There are 3 Releases- Release 1-MVP, Release 2, and Release 3 (All contained in the dropdown menus in Column D) -Release 1-MVP can only have 10 user stories -Release 2 can only have 10 user stories -Release 3 can only have 5 user stories -All remaining user stories are assigned to "Backlog for Future Release" Hints/Tips: -Question if a user role has too much functionality to be in the MVP release. -Question what is a nice-to-have vs high-value based on the scenario and vision. -Question if you should trade off- what is the worst thing that could happen if the user had to wait for that functionality to come later. -Refine, rewrite, or delete a user story in the blue user story tab if it doesn’t fit into your Release or MVP plan
Role | User Story | Acceptance Critieria | Sprint | Release 1-MVP Total Stories =10 | Release 2 Total Stories =10 | Release 3 Total Stories =5 | Backlog for Future Release
CDC Official | As a CDC Official I can view the number of patients that have reported testing positive so that so that I can analyze the outbreak . | -Patient names are anonymous -User can see a summary of the numbers provided -User must be logged in from a government IP address to view |  | 0 | 0 | 0 | 0
CDC Official | As a CDC Official I can see a report of the # of test kits that health care companies have created so that that I can send funding. | -User can see a summary of the total number of test kits -User can see a summary of the number of test kits produced by healthcare company -User can see the names of the health care company -User can see amount of funds sent to each health care company
Doctor | As a Doctor I can add the name of patients I have treated so that I can add treatments . | -Alpha Numeric characters are allowed -Patient First and Last Name required -Patient DOB required -Patient Location Required -Patient Gender is optional
Doctor | As a Doctor I can login to the system so that I can enter patient treatment information. | -User name and email address required -User is locked out after 3 incorrect entries
Healthcare Company | As a Healthcare Company I can add the number of test kits produced so that the CDC can determine where test kits should be sent. | -Only numeric characters allowed -User can see data that previously entered
Healthcare Company | As a Healthcare Company I can reset my password by myself so that that I can login again. . | -User must verify email address -User must verify answer security question to reset password
Medical Examiner | As a Medical Examiner I can add a person's gender so that deaths can be tracked by gender . | -User can select from list of genders -User can update gender selection -Users gender selection is not shared with CDC Officials
Medical Examiner | As a Medical Examiner I am automatically logged out of the system so that no one can access my account. | -Timeout occurs after 15 mins of inactivity -After timeout user is returned to login page
Patient | As a Patient I can change my test results so that the system data is accurate. | -User can modify test results twice -Doctors are notified when a patient changes test results
Patient | As a Patient I can enter any stores that I visited 3 days before testing positive so that others are aware of their potential exposure to the virus. | -Option only visible for patients that report positve test -Can specify store name, date entered, city, and state
System Administrator | As a System Administrator I can give access to the system so that users can access,import, share data.. | -First and Last Name required -Enter email addresses -Gmail email address are not allowed access
System Administrator | As a System Administrator I can remove access so that users are not able to access the system. | -Removed user recieves email confirmation of removal -Removed user can't login once removed -System administrator must confirm the user that they are removing before leaving the page
Test Center | As a Test Center I can update/change the number of test kits recieved so that data is accurate. | -Only allow update one time -Make user confirm change before leaving the page
Test Center | As a Test Center I can I want to be notified when my stock falls before a certain level, so that I can proactively order additional testing supplies. | -System notifies user by email -User can set number that stock must reach for email to be sent -System notifies user upon login that stock is low
Patient | As a Patient I can report that I contracted the virus so that data is accurate. | 1) System confirms the report to the user by email 2) System explains to the user how to read general medical advices provided
Patient | As a Patient I can read general advice written by professionals so that I always have a medical reference about symptoms and potential cure / behavior to adopt. | 1) System allows to search for the symptoms 2) System provides a hotline number for emergencies
CDC Official | As a CDC Official I can see the heat maps of the outbreak so that new proactive strategies can be planned accordingly. | 1) User can search for town / area, System will show it on the map 2) System allows to zoom in / out
CDC Official | As a CDC Official I can send funding to a specific area so that funds can be used to stop the virus spreading in that area. | 1) User can start the fund sending process directly from the heat maps report 2) User has a report page containing all the funds sent previously
Doctor | As a Doctor I can report the number of death caused by the virus so that data is accurate. | 1) User can report the number of death caused by virus 2) User can generate reports relate to the number of death caused by the virus for the previous months / years
Doctor | As a Doctor I can write and update professional medical advice that will be available to patients so that patience have a medical reference about symptoms and potential cure / behavior to adopt. | 1) User can create / delete / update the provided medical advice 2) User can check the previous version of a medical advice in the medical advice's history
Healthcare Company | As a Healthcare Company I can report a change in the expected future production of tests so that the CDC can take corrective actions in advance. | 1) Healthcare company can report a problem in production that can lead to a different number of test produced 2) Healthcare company can update the reported problem in case of change
Healthcare Company | As a Healthcare Company I can so that .
Medical Examiner | As a Medical Examiner I can so that .
Medical Examiner | As a Medical Examiner I can so that .
System Administrator | As a System Administrator I can so that .
System Administrator | As a System Administrator I can so that .
Test Center | As a Test Center I can so that .
Test Center | As a Test Center I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .
As a I can so that .

## Release Plan & MVP Plan
Instructions: Create a Release & MVP Plan in this sheet. Copy your 10 Release 1-MVP user stories into column A, Rows 3-12 in the Release & MVP plan template Copy your 10 Release 2 user stories into column A, Rows 13-22 in the Release & MVP plan template Copy your 5 Release 3 user stories into column A, Rows 23-27 in the Release & MVP plan template
Releases | Sprints | User Story | Story Points
Release 1- MVP | Sprint 1 |  | 2
3
3
| Sprint 2 |  | 5
0.5
2
0.5
| Sprint 3 |  | 5
2
1
Release 2 | Sprint 4 |  | 5
0.5
1
1
0.5
| Sprint 5 |  | 1
2
2
1
3
Release 3 | Sprint 6 |  | 3
5
| Sprint 7 |  | 2
0.5
5